Client Onboarding SOP — From Signed Contract to First Content

Ultimate AI SMMA OS | Complete 30-Day New Client Onboarding Process

# Why Onboarding Defines the Relationship

The onboarding experience a new client has with your agency determines whether they stay 3 months or 3 years. A disorganized, reactive onboarding signals to clients that the chaos will continue. A systematic, proactive onboarding builds immediate confidence and sets the tone for a professional, long-term relationship. This SOP covers every step of your onboarding process from day zero through the delivery of your first content.

# Day 0 — Contract and First Payment

Send signed contract via DocuSign, PandaDoc, or HelloSign — never paper-only

Issue first invoice immediately upon contract execution

Send welcome email (use Welcome_Email_Sequence.docx Email 1 as template)

Create client folder in Google Drive / Notion with: Brand Assets, Content Library, Reports, Contracts

Add client to your CRM (Notion Client_Database.csv) and mark status as 'Onboarding'

Set calendar reminders: 7-day kickoff, 14-day first check-in, 30-day first report

# Days 1-5 — Information Gathering

Send Brand_Discovery_Questionnaire.docx to client — set a 5-day response deadline

Send Platform_Access_Setup_Guide.docx to client for granting access

Request brand assets: logo files (PNG + SVG), brand colors (hex codes), font names

Request any existing content: photos, videos, old social posts to keep or repurpose

Request competitor names and any 'inspiration accounts' they like

Request access to: Meta Business Manager, Google Analytics, any existing scheduling tools

# Days 5-10 — Strategy Development

Complete Social_Media_Audit_Template.xlsx for all the client's current platforms

Research 5 competitors using the Competitor Analysis tab

Define 3-5 content pillars based on questionnaire responses and niche research

Define posting frequency per platform based on package tier

Build hashtag bank (50 hashtags per platform) using Hashtag_Strategy_Guide.docx

Draft Month 1 content themes and create the first content calendar frame

# Days 10-14 — Kickoff Call

Kickoff Call Agenda (45 minutes):

5 min: Introductions, welcome, confirm communication preferences

10 min: Present your audit findings from Social_Media_Audit_Template.xlsx

10 min: Present your 3-month social media strategy and content pillars

5 min: Walk through the content approval workflow — how reviews will work

5 min: Clarify any outstanding questionnaire items or asset requests

5 min: Set expectations — what they can expect and when, response times, revision policy

10 min: Q&A — let the client ask everything they have

Post-Call Actions:

Send meeting notes within 24 hours

Begin content creation immediately after kickoff

# Days 14-25 — First Content Batch

Create Month 1 content using AI_Prompt_Library.docx and Content_Creation_SOP.docx

Design all graphics using client's brand kit in Canva

Write all captions using Caption_Writing_Framework.docx

Conduct internal quality review against Agency_SOPs_Master_Guide.docx standards

Share content calendar with client via Notion, Google Sheets, or PDF

Allow 5 business days for client review and revision requests

# Days 25-30 — First Publishing Cycle

Process all revision requests within 48 hours

Obtain written approval ('Looks good!' or 'Approved' message is sufficient) before scheduling

Schedule all approved content in Buffer/Hootsuite/Later

Publish first post and send client a 'Your first post is live!' message

Begin community management monitoring immediately after first post

Day 30: Send 1-month check-in message asking for feedback on the process