Onboarding Checklist SOP

Bookkeeping Business Operating System | Client Onboarding

# DAY 1 — AGREEMENT SIGNED

[ ] Send welcome email with intake form link

[ ] Create client record in practice management system

[ ] Set up client folder (cloud storage)

[ ] Schedule kickoff call within 3–5 days

# DAYS 2–3 — INTAKE FORM RECEIVED

[ ] Review intake form for completeness

[ ] Request access to accounting software

[ ] Request access to bank/credit card feeds

[ ] Request prior bookkeeper files if applicable

[ ] Note catch-up scope and quote if needed

# DAYS 3–5 — KICKOFF CALL

[ ] Log in to accounting software before call

[ ] Complete kickoff call using Kickoff Call Script

[ ] Confirm services, delivery date, and communication method

[ ] Send post-kickoff email summary

# WEEK 1 — INITIAL SETUP

[ ] Review and clean up chart of accounts

[ ] Connect all bank and credit card feeds

[ ] Review prior period transactions for context

[ ] Document client-specific categorization notes

[ ] Begin current month reconciliation

# FIRST REPORT DELIVERY

[ ] Complete all reconciliations

[ ] Run P&L and Balance Sheet

[ ] Write monthly summary notes

[ ] Send first report email using template

[ ] Schedule 15-minute review call if desired